## Bug Report
Bug ID | Test case ID | Title | Description | Stepts to Reproduce | Expected Result | Actual Result | Priority | Severity
B1_TC_02_01 | TC_02_01 | Inappropriate title and description of products | Title and description of some products are inappropriate. Product image shows orange T-shirt but title says “Red”. This mismatch leads to user confusion and data inconsistency. | inconsistency. 1. Go to Product Page 2. Check product titled “Red T-shirt” 3. Observe product color in image 4. check other product's description too | Product title , description and image color should be consistent. | Title says “Red” but image shows “Orange” and description mismatch | P0 | mid
B2_TC_02_03 | TC_02_03 | Filter dropdown does not open when clicking dropdown arrow icon | The filter dropdown on the Products page opens only when clicking the text (“A to Z”), but does not open when clicking the arrow icon beside it. This causes usability issues for users expecting both areas to trigger the dropdown. | 1. Log in to SauceDemo. 2. Go to the Products page. 3. Try clicking the dropdown arrow beside “Name (A to Z)”. | Clicking either text or arrow should open the filter list. | Clicking text opens dropdown, but clicking arrow icon does nothing. | P2 | low
B3_TC_CART_05 | TC_CART_05 | No option to change product quantity in cart | The cart page displays all added products but lacks an option to increase or decrease item quantity | 1. Add one or more products to the cart. 2. Navigate to the Cart page. 3. Look for options (e.g., +/− buttons or input field) to change product quantity. | Cart page should allow modifying product quantity via +/− buttons or a numeric input box. | Quantity cannot be modified — only remove option is available. | P0 | mid
B4_TC_CART_07 | TC_CART_07 | Invalid product ID adds broken entry to cart causing empty cart page | When accessing a product page using an invalid product ID (e.g., id=13263623), the system shows “Item not found.” However, clicking Add to Cart still increases the cart badge count by 1. On opening the cart, a blank or non-functional cart page appears. This breaks the entire cart flow. | 1. Navigate to URL: https://www.saucedemo.com/?/inventory-item.html&id=13263623 2. Observe that the page displays “Item not found” message. 3. Click Add to Cart (if button is visible). 4. Check cart badge count. 5. Click Cart icon and view cart page. | The system should disable the Add to Cart button for invalid items and prevent them from being added to the cart. | Cart badge increases, but cart page becomes blank/unresponsive. | P0 | high
B5_TC_CART_08 | TC_CART_08 | Logout and re login (different user) not Changing the cart information | After logging out from one user account and logging in with a different user, the previous user’s cart items are still displayed in the cart. | 1.Log in to https://www.saucedemo.com with User A. 2.Add one or more items to the cart. 3.Log out from User A. 4.Log in again using User B credentials. 5.Go to the Cart page. | Cart should show User B’s cart items only.Cart data from User A must be cleared automatically upon logout. | After logging in as User B, the same cart items from User A are still displayed | P0 | high
B6_TC_CHECKOUT_02 | TC_CHECKOUT_02 | User is able to proceed to checkout with an empty cart | When a user tries to proceed to checkout without adding any items to the cart, the application still allows navigation to the checkout page. | 1.Log in to https://www.saucedemo.com 2.Do not add any items to the cart. 3.Click the Cart icon to open the cart page. 4.Click the Checkout button. | Checkout button should be disabled, or System should show an alert/error message such as “Your cart is empty. Please add items before checkout.” | The system allows the user to proceed to the checkout page even when the cart is empty. | P1 | mid
B7_TC_CHECKOUT_08 | TC_CHECKOUT_08 | Cancel button redirects to Home page instead of Cart page | When a user clicks the “Cancel” button during the checkout process, the system redirects them to the Home (Products) page instead of returning them to the Cart page. | 1.Log in to https://www.saucedemo.com 2.Add one or more products to the cart. 3.Go to the Cart page and click Checkout. 4.On the checkout information or summary page, click the Cancel button. | Clicking the Cancel button should return the user to the Cart page, preserving previously added items. |  | P2 | mid
B8_TC_LOGOUT_05 | TC_LOGOUT_05 | After logout , system does not hold user/cart information | After logging out from one user account and logging in with a different user, the previous user’s cart items are still displayed in the cart. | 1.Log in to https://www.saucedemo.com with User A. 2.Add one or more items to the cart. 3.Log out from User A. 4.Log in again using User B credentials. 5.Go to the Cart page. | Cart should show User B’s cart items only.Cart data from User A must be cleared automatically upon logout. | After logging in as User B, the same cart items from User A are still displayed | P0 | high